## Summary
Gesture Pipeline Tracker
PetalEdge motion gesture recognition - remaining work, per Motion recognition/motion_roadmap.md. Hours = AI-assisted session time (1 dev, Claude Pro + Antigravity Pro), calibrated against this repo's own git history (Phase 0: 5 batches in ~5h50m, one day). See the Tasks sheet for what each row actually is, and Glossary for the terms used throughout.
81.0h |  | 0h |  | 81.0h
MVP planned |  | MVP done |  | MVP remaining
20.2d |  | 0% |  | 95h
Remaining, workdays (4h focused/day) |  | MVP % complete |  | Post-MVP (rough, uncommitted)
Phase | Title | What it adds | MVP? | Planned (h) | Done (h) | Remaining (h) | % done
0 | Project Type Foundation & Shared-Page Architecture | A Project.project_type column and one shared dashboard that branches its content by type, so Motion and Object Detection stop competing for the same UI. | Yes | 0 | 0 | 0 | 100%
1 | Device Connection & Live Acquisition | A single, official Motion USB workflow - connect a board, watch its live signal, record a labelled sample, land it in the dataset - with no second workflow anywhere else in the app. | Yes | 15.5 | 0 | 15.5 | 0%
2 | Motion Dataset Management | Recordings from Phase 1 become browsable, viewable as a waveform, labellable and importable. Nothing is computed from them yet - that starts in Phase 3. | Yes | 8.5 | 0 | 8.5 | 0%
3 | Window Generation | Segments one long recording into many overlapping fixed-length windows, so a single 10-second capture yields many training examples instead of one. The first genuinely new DSP stage in the whole roadmap. | Yes | 9 | 0 | 9 | 0%
4 | Processing Blocks | Makes the three existing MVP processing blocks (Raw Data, Spectral Analysis, Flatten) produce physically meaningful output on multi-axis accelerometer/gyroscope windows - no new blocks, no pipeline redesign. | Yes | 4 | 0 | 4 | 0%
4.5 | DSP UI & Edge-Impulse-style Integration | The actual Parameters and Generate-features screens for the three MVP processing blocks, wired to the DSP backend that already exists, including the Normalize features control. | Yes | 6.5 | 0 | 6.5 | 0%
5 | Core Feature Generation Backend | Makes windowed motion features actually flow into the same features.npz cache the training worker already reads - with correct provenance, correct cache invalidation, real cancellation, and Standardize normalization statistics stored alongside the dataset. | Yes | 6.5 | 0 | 6.5 | 0%
5.5 | Advanced DSP Backend Services | Every backend service the full DSP UI needs that isn't feature generation itself, so every honest-degraded control Phase 4.5 shipped flips to live. | Yes | 6 | 0 | 6 | 0%
6 | Neural Network Training | Trains gesture classifiers with neural networks (Dense, Conv1D, Conv2D, LSTM only - no classical ML in the MVP) from the windowed feature cache, on the existing Keras/TensorFlow training pipeline. | Yes | 7 | 0 | 7 | 0%
7 | Evaluation | Reports motion classifier accuracy at the level users actually care about - per recording, not only per window - and states how the model was trained, reusing the existing evaluation surface. | Yes | 3.5 | 0 | 3.5 | 0%
7.5 | Live Classification | Runs a trained motion model against a live USB sensor stream in real time - point a board at the model you just evaluated and watch it classify - on the Live Classification surface PetalEdge already ships. | Yes | 5.5 | 0 | 5.5 | 0%
7.6 | Model Testing | The offline counterpart to Live Classification: run the model over saved or uploaded recordings and see exactly where it was right, wrong, and how confident it was - per window and per recording. | Yes | 4 | 0 | 4 | 0%
8 | Deployment | Ships a trained motion classifier to hardware through the deployment pipeline that already exists, with enough metadata that on-device windowing, DSP and normalization reproduce training exactly. Completes the MVP. | Yes | 5 | 0 | 5 | 0%
9 | BLE & Smartphone Connectivity | Collect motion data wirelessly - from a BLE board and from a smartphone's own accelerometer/gyroscope - on the existing WebSocket streaming architecture, unchanged. | No | 23 | 0 | 23 | 0%
10 | Future AI Enhancements | Deferred MODEL and learning-task capabilities, recorded so they aren't designed for prematurely: classical ML (Random Forest, SVM, Logistic Regression, XGBoost), TinyML optimization, BYOM/ONNX import, regression, anomaly detection, sensor fusion, audio recognition. | No | 40 | 0 | 40 | 0%
11 | Advanced Connectivity & Platform Expansion | Deferred CONNECTIVITY and platform-scale capabilities beyond Phase 9's two transports: Wi-Fi, an MQTT bridge, multi-device/fleet/remote management, advanced OTA, enterprise connectivity, and a Redis-backed StreamStore for distributed deployments. | No | 32 | 0 | 32 | 0%
| TOTAL (MVP, Phases 0-8) |  |  | 81 | 0 | 81

## Tasks
Phase # | Phase | MVP? | Task | Layer | Status | Hours | Days (4h/day) | Objective - what it does & why | Key deliverables | Definition of done | Notes / risk
0 | Project Type Foundation & Shared-Page Architecture | Yes | Project type schema, creation UI, block filtering, six-surface branch | Both | Done | 0 | 0 | Give every project a project_type (object_detection ¦ motion) chosen at creation, and branch all six shared dashboard pages (Dataset, Impulse, Training, Model Testing, Deployment, Labeling) on it - one route, one nav, no duplicate pages. | Project.project_type column + migration 0033_project_type; POST /projects create/validate/default; CreateProjectModal two-card picker; ObjectDetection<X>/Motion<X> content-component pairs for all six surfaces; _BLOCKS_BY_PROJECT_TYPE filtering on both DSP catalog routes. | All 16 acceptance criteria in motion_phase0.md re-verified: one nav for both types, motion shows only motion DSP/learning blocks (raw/flatten/spectral_analysis; dense/conv1d/lstm/anomaly_gmm) and vice versa, every pre-existing project reads back object_detection. | Batches 1-5 complete. Actual: ~5h50m session time in one day (04 Sep, git 1cc905e..7e26660).
1 | Device Connection & Live Acquisition | Yes | Batch 1 - Dataset-page "Connect Device" UI on MotionConnectionService | Frontend | Done | 0 | 0 | Give Motion projects one entry point for connecting a USB board, built against a placeholder service interface so the UI could ship before the real transport existed. | USBConnectionDialog, SupportedDeviceList/Card, EmptyState, DeviceInfoCard, ConnectionStatusBadge, boards.ts (real Arduino/Raspberry Pi vendor IDs), the MotionConnectionService interface (scanDevices/connect/disconnect/getDeviceInfo/getSensors). | Connect Device opens on /dashboard/data/dataset, lists supported boards, and a connected device's identity renders in DeviceInfoCard - on the mock service. The competing Devices-page draft (useWebSerial.ts) was retired so only this workflow exists. | Shipped, then consolidated into the single app-wide USB workflow.
1 | Device Connection & Live Acquisition | Yes | Batch 2 - real Web Serial implementation behind MotionConnectionService | Frontend | Done | 0 | 0 | Replace the placeholder service with a real navigator.serial transport behind the exact same interface, so nothing above it (the UI shells) has to change. | createWebSerialMotionConnectionService() in webSerialTransport.ts; requestDevice() added to the interface (Web Serial needs a distinct user gesture to authorize a never-before-seen board); web-serial.d.ts ambient types; devicesApi.heartbeat() called via raw axios (not the shared api instance) so a device-key 401 can't force-log the user out. | USBConnectionDialog drives a real port request -> identity probe -> hello/hello-ack -> heartbeat over /ws/device, with no mock code path reachable from the UI. Verified up to the browser's native picker (no physical board in the build environment). | Completed - createWebSerialMotionConnectionService() replaces the mock; requestDevice() added.
1 | Device Connection & Live Acquisition | Yes | Batch 3 - live sensor streaming over /ws/device | Backend | To do | 4 | 1 | Let a connected device push live IMU frames to the backend and have them fanned out in real time, without persisting anything - the server half of the live-preview contract. | StreamType.sensor + 3 EVENT_SENSOR_* studio events; POST /devices/{pk}/streams/sensor/start¦stop; app/motion/api/streams.py, .../services/stream_control.py, .../websocket/sensor_frames.py (takes no db argument - the enforcement that preview is never persisted), .../services/frame_codec.py. | 500 streamed sensor-frame messages leave Sample/FeatureSet/object-storage counts unchanged; starting a sensor stream during an active snapshot stream returns 409; snapshot/inference streams behave identically to today. | Mirrors the existing /devices/{pk}/streams/* shape exactly.
1 | Device Connection & Live Acquisition | Yes | Batch 4 - live signal chart driven by Batch 3's stream | Frontend | To do | 2 | 0.5 | Render the live IMU stream on the Dataset page in real time, so a user can see their sensor is actually producing data before recording anything. | SignalPreview.tsx - rolling multi-axis recharts chart with a fixed-size ring buffer and rAF-throttled repaint; streamSensorStart/Stop in api.ts; Start/Stop streaming controls beside the connected device. | Live IMU data is visible in real time; Stop halts frames within one keepalive interval; nothing is written to the database; MotionConnectionService's public interface is unchanged (confirmed by diff).
1 | Device Connection & Live Acquisition | Yes | Batch 5 - stop-recording + duration_ms on the sampling pipeline | Backend | To do | 2 | 0.5 | Finish the recording path that already exists end to end (start-sampling -> sample-* -> signed upload -> Sample row) by letting it be stopped cleanly, and fix duration_ms, which is NULL on every device-recorded sample today. | build_stop_sample() beside build_stop_snapshot(); duration_ms populated in process_ingestion; app/motion/api/recording.py (POST /devices/{pk}/stop-sampling); app/motion/services/recording.py. | stop-sampling ends an in-flight recording (409 if not sampling); the resulting sample carries correct sensor_type/frequency_hz/num_channels/num_samples AND duration_ms; no second sampling service or ingestion route was created.
1 | Device Connection & Live Acquisition | Yes | Batch 6 - recording controls on /dashboard/data/dataset | Frontend | To do | 2 | 0.5 | Let a user start and stop a labelled recording directly from the page they already connected their device on, so it becomes a normal Sample with no second workflow. | Start/Stop recording controls calling the existing start-sampling route and Batch 5's stop-sampling route; stopSampling(pk) in api.ts; sample-list refresh on completion. | A labelled recording started from the Dataset page is returned by GET /samples/project/{id} alongside uploaded CSV samples; Stop discards a partial sample rather than persisting it; no new route or page was added.
1 | Device Connection & Live Acquisition | Yes | Batch 7 - connection recovery, conflict handling, frequency validation | Both | To do | 4 | 1 | Make every failure mode in the connection lifecycle - port loss, stream conflicts, mid-recording disconnect, an unsupported sample rate - produce a defined outcome instead of a hang or a silent partial write. | assert_frequency_supported() in shared app/services/devices.py; sample.failed emission on disconnect-while-sampling; app/motion/services/validation.py (axis-count consistency, length_ms bounds); Web Serial reconnect-with-backoff inside MotionConnectionService; stream-conflict 409s; preview auto-pauses during recording and resumes after. | An unsupported frequency returns 422; unplugging mid-recording produces sample.failed and no partial Sample row; reconnecting the same board resumes the same Device row; every existing camera-flow status code is unchanged. | Edge-case heavy - real disconnect/reconnect timing needs a live session to verify, not just code review.
1 | Device Connection & Live Acquisition | Yes | Batch 8 - animation, loading states, responsive layout, a11y | Frontend | To do | 1.5 | 0.38 | Make the motion acquisition surfaces feel finished and visually match Object Detection - appearance and interaction only, no behavior change. | Recording countdown/elapsed timer; status pills (connected/streaming/recording/error) via ConnectionStatusBadge; skeleton/loading states on every async surface from Batches 2-7; a specific message for every Batch 7 failure mode, replacing generic toasts. | Motion components are visually indistinguishable in style from Object Detection's; every animation is transform/opacity/filter only and honours prefers-reduced-motion; zero backend files touched.
2 | Motion Dataset Management | Yes | 2.1 Dataset Explorer | Frontend | To do | 1.5 | 0.38 | Browse motion recordings in the existing dataset page the same way image samples are browsed today. | Recordings list/grid view reusing the existing Sample-browsing components. | A motion project's dataset page lists its recordings with the same filter/sort affordances Object Detection already has. | No backend work - browses existing Sample rows.
2 | Motion Dataset Management | Yes | 2.2 Signal Viewer - per-recording waveform | Both | To do | 2.5 | 0.62 | Let a user see the actual signal shape of a recording before deciding to label or discard it. | One new read endpoint serving raw sample data for charting; a waveform preview component per recording. | Opening a recording renders its multi-axis waveform; the one new endpoint is read-only and adds no write path. | One new read endpoint - the only new backend route in all of Phase 2.
2 | Motion Dataset Management | Yes | 2.3 Label Management - assign, relabel, bulk, split | Frontend | To do | 2.5 | 0.62 | Give motion recordings the same label-management affordances Object Detection samples already have. | Assign/relabel controls, bulk relabel, bulk delete, train/test split - built on the existing labelsApi/samplesApi CRUD, no new backend. | A user can assign, bulk-relabel, bulk-delete and split motion recordings with no dedicated motion backend route.
2 | Motion Dataset Management | Yes | 2.4 Import Validation - CSV/JSON become correct Sample rows | Backend | To do | 2 | 0.5 | Make an uploaded CSV/JSON motion file become a correctly-shaped Sample row - right sensor_type, axis count and frequency - instead of a malformed one. | Two modifications to the existing import/upload path validating shape and metadata before persisting. | A malformed or mismatched-axis-count file is rejected with a clear error rather than silently ingested as a bad Sample row.
3 | Window Generation | Yes | Windowing module + windowed dsp_worker | Backend | To do | 9 | 2.25 | Add the windowing stage that does not exist anywhere in the repository today: slice a recording into overlapping windows per Impulse.window_size_ms/window_increase_ms, and route each window through the existing DSP block pipeline as if it were its own sample. | New backend/app/motion/dsp/windowing.py (kept out of app/ml/dsp/ deliberately - see Architecture Principle in motion_phase3.md); dsp_worker gains a windowed code path used only when the impulse is time-series. | An existing image impulse regenerates a byte-identical features.npz (the roadmap's universal acceptance criterion); a motion recording produces the expected number of overlapping windows; the windowing gate is explicit and project_type-free. | Largest genuine gap in the roadmap; byte-identical-features requirement means real regression runs, not just a code read.
4 | Processing Blocks | Yes | Per-axis Spectral Analysis / Raw / Flatten correctness | Backend | To do | 4 | 1 | Stop Spectral Analysis from interleaving axes before its FFT - today a 3-axis (N,3) window is flattened to x0,y0,z0,x1,... before the transform, which is wrong for motion even though it's harmless for the single-channel audio case the code was written for. | Per-axis FFT dispatch in processor.py's _spectral_analysis; Raw/Flatten reviewed for the same multi-axis-correctness issue. | MFCC and spectrogram outputs stay bit-identical (the roadmap's universal criterion); a 3-axis window's spectral features are computed per axis, not interleaved. | Numeric correctness - needs real before/after signal comparisons, not just a diff read.
4.5 | DSP UI & Edge-Impulse-style Integration | Yes | Parameter UI for the 3 motion blocks + Generate Features page + Normalize toggle | Frontend | To do | 6.5 | 1.62 | Build the Edge-Impulse-style Parameters and Generate-features surfaces for Raw Data, Spectral Analysis and Flatten, and state explicitly, control by control, anywhere the backend does not yet reach a control (an honest degraded state, never a control that silently does nothing). | Per-block parameter forms; a Generate Features page (progress, log streaming, cancel); the Normalize features (none ¦ standardize) toggle stored at dsp_blocks[i].params.normalize_features. | Every one of the three blocks has a working Parameters screen; Normalize features defaults to none and is declared only on the three motion blocks, never on image.
5 | Core Feature Generation Backend | Yes | Window provenance, config hash, cancellation, persisted logs, Standardize normalization | Backend | To do | 6.5 | 1.62 | Make the Phase 4.5 Generate-features page produce a real feature dataset: dispatch a run, report real progress, stream real log lines, be cancelled and stay cancelled, and finish with a features.npz the training worker accepts unmodified. | Window provenance recorded per feature row; a widened config hash that invalidates the cache correctly on parameter change; working job cancellation; persisted log lines via the new nullable dsp_feature_jobs.log_lines column; Standardize normalization (per-feature zero mean/unit variance fitted on the training split, stored in meta_json['normalization']). | A none-normalization run produces a byte-identical features.npz to today (the roadmap's universal criterion); a standardize run's statistics are recoverable from meta_json; this migration is the only schema change after Phase 0 in the entire roadmap.
5.5 | Advanced DSP Backend Services | Yes | Feature Explorer, Feature Importance, log detail, on-device performance, DSP preview | Backend | To do | 6 | 1.5 | Implement the five service areas the Phase 4.5 UI is waiting on: Feature Explorer analytics, Feature Importance, detailed Processing Logs, On-device Performance estimation, and DSP Preview enhancements. | Backend endpoints for each of the five service areas, plus any shared API the Phase 4.5 UI needs that Phase 5 didn't already provide. | Every control in Phase 4.5 that shipped in a stated degraded state now has a live backend behind it, with no change to Phase 5's feature-generation output.
6 | Neural Network Training | Yes | Architecture editor - Dense, Conv1D, Conv2D, LSTM + layer validation | Both | To do | 7 | 1.75 | Let a user pick a learning block, edit its layers, set training cycles/learning rate/processor, start a run, watch a live epoch chart, and finish with a TrainedModel the evaluation and deployment pages already understand - through the existing run_training_job task. | New app/ml/training/layer_spec.py (the one net-new backend module besides windowing.py in the whole roadmap); a layer-editing UI with per-architecture validation for Dense/Conv1D/Conv2D/LSTM. | A gesture dataset trains end to end on a neural network; FOMO/YOLO-Pro/SSD training metrics are unchanged (universal criterion); build_model still returns a keras.Model for every architecture.
7 | Evaluation | Yes | Recording-level aggregation, Training Summary, model comparison | Both | To do | 3.5 | 0.88 | A model predicts per window, but a user records per gesture - report both numbers, with the per-recording one as the headline, and disclose how the model was trained (normalization, config) on the same page. | Window-to-recording aggregation logic; a Training Summary panel showing normalization/config disclosure; model comparison reusing the existing evaluation surface. | A trained motion model's evaluation page shows accuracy per recording (not just per window) and states its training configuration; no field in this phase distinguishes a model engine (neural networks only).
7.5 | Live Classification | Yes | Real-time inference on the live stream, confidence viz, prediction timeline | Both | To do | 5.5 | 1.38 | Cut windows from the live stream, score each one against the resolved TFLite model, and show a labelled prediction with a confidence readout and a rolling timeline - in a session the user explicitly starts and stops. | Windowing-from-live-stream logic reusing Phase 1's sensor stream; confidence visualization and prediction timeline on the existing /dashboard/impulse/live-classification page; session start/stop controls. | A live gesture produces a live prediction with no new page, no new worker, no new table; image-impulse Live Classification behaves identically before and after this phase (universal criterion). | Real-time-on-a-live-stream can't be sped up by AI - needs an actual board and real clock time to confirm.
7.6 | Model Testing | Yes | Inference over saved/uploaded recordings, misclassification analysis | Both | To do | 4 | 1 | Let a user pick recordings the model has never been graded on - or upload new ones - press Classify all, and browse per-window and per-recording predictions with confidences and misclassifications. | Wiring the existing model_testing_service/model_testing_worker to motion TFLite artifacts; misclassification-analysis view on the existing Model Testing surface. | A user classifies a batch of recordings and browses results with no new page, worker, queue or table; image-impulse Model Testing is unaffected (universal criterion).
8 | Deployment | Yes | Manifest motion params, normalization export, MCU compatibility gate | Both | To do | 5 | 1.25 | Export a Dense/Conv1D/Conv2D/LSTM model as TensorFlow Lite through the existing pipeline, with window size, DSP params and normalization statistics carried through the manifest so on-device inference reproduces training - and refuse spectral_analysis on an MCU target with a stated reason rather than silently mis-deploying it. | Motion params added to the deployment manifest; normalization mean/std exported and applied on-device; a compatibility gate that refuses unreachable MCU/DSP-block combinations before the build starts. | A trained motion model deploys through the same page/routes/worker/compatibility-service as Object Detection; no sklearn artifact path exists (neural networks + TFLite only); the MVP end-to-end path (create project -> connect device -> record -> window -> DSP -> train -> evaluate -> classify/test -> deploy) is complete. | Completes the MVP end to end.
9 | BLE & Smartphone Connectivity | No | BLE pairing/streaming, smartphone DeviceMotion capture, transport picker | Both | To do | 23 | 5.75 | A gesture recorded over BLE or captured on a phone must land as a Sample row indistinguishable from the same gesture recorded over USB - same table, same sensor_type/frequency_hz/num_channels, same DSP and training path. If the two differ, the transport leaked into the data, which this phase exists to prevent. | BLE pairing and GATT streaming for a Nano 33 BLE Sense untethered from USB; smartphone DeviceMotion capture; a transport picker alongside the existing USB flow. | A BLE- or phone-captured recording is byte-for-byte indistinguishable in shape from a USB one through the entire downstream pipeline. | Rough - BLE/GATT is protocol- and hardware-bound, slower to compress.
10 | Future AI Enhancements | No | Classical ML (RF / SVM / LogReg / XGBoost), TinyML, BYOM/ONNX, regression, anomaly, fusion | Both | To do | 40 | 10 | Open non-Keras model kinds only after the complete neural-network pipeline (Phases 6-8) ships. No MVP phase trains, evaluates, tests or deploys a non-Keras estimator - this phase is where that door opens, if it opens. | Not committed. Recorded per-item in motion_phase10.md with its integration point and the one thing that would force a change to earlier phases if pulled forward. | Not applicable - a planning register, not a build target, until individually greenlit. | Rough order-of-magnitude estimate.
11 | Advanced Connectivity & Platform Expansion | No | Wi-Fi, MQTT bridge, fleet / remote device management, OTA, Redis StreamStore | Both | To do | 32 | 8 | Every transport in this phase terminates in the same hello/sensor-frame/start-sample WebSocket contract Phase 9 relies on, so none of it requires a new protocol - only new carriers for the existing one, plus the multi-instance/Redis work needed to run it at fleet scale. | Not committed. Recorded per-item in motion_phase11.md with its integration point and the one thing that would force a change to earlier phases if pulled forward. | Not applicable - a planning register, not a build target, until individually greenlit. | Rough order-of-magnitude estimate.

## Glossary
Glossary
Terms used consistently across every phase document in Motion recognition/. Source: motion_roadmap.md §3 and each phase's own spec.
Term | Meaning
Project type | Project.project_type in {object_detection, motion}, NOT NULL. Selects which content the shared dashboard pages render - a presentation field only, never read by the pipeline. Written once at project creation; every pre-existing project is backfilled to object_detection. No third/nullable state. Introduced in Phase 0.
Modality | Impulse.input_type in {time-series, image, custom}. Drives actual pipeline behavior (unlike project type, which is presentation-only). Pre-existing, not introduced by this roadmap.
Recording | One captured motion signal. Persisted as a Sample row - there is no separate recording table.
Window | A fixed-length slice of a recording, produced by Phase 3. Derived at feature-generation time, never persisted as its own row.
Feature vector | One window after all DSP blocks have run on it. One row of X in features.npz.
Pre-existing project | A project created before Phase 0 shipped. No separate legacy state or compatibility mode - migration 0033_project_type backfills every such row to object_detection, so it behaves exactly like an Object Detection project created today.
Normalize features | The DSP option at dsp_blocks[i].params.normalize_features. Exactly two values: none (default, today's behavior) and standardize (per-feature zero mean / unit variance, fitted on the training split). Control ships in Phase 4.5, computed and stored in Phase 5, exported and applied on-device in Phase 8.
Normalization statistics | The fitted per-feature mean and std, persisted in meta_json['normalization'] inside features.npz. Distinct from any display statistic computed for axis ranges.
Neural network model | A Keras model from Phase 6 - Dense, Conv1D, Conv2D or LSTM - persisted as model.keras plus float32/int8 .tflite variants. The only model kind the MVP trains, evaluates, classifies and deploys.
Live Classification | Real-time inference on a live USB sensor stream (Phase 7.5), on the existing /dashboard/impulse/live-classification surface. Nothing is persisted.
Model Testing | Offline inference over saved or uploaded recordings (Phase 7.6), on the existing Model Testing surface and its ModelTestRun/ModelTestSample rows.
MotionConnectionService | The single frontend interface (scanDevices, connect, disconnect, requestDevice, getDeviceInfo, getSensors) every USB workflow in the app is built against. Batch 1 (Phase 1) shipped it against a mock; Batch 2 replaced the mock with a real navigator.serial (Web Serial) implementation behind the same interface - nothing above it changed.
StreamStore | The existing in-memory (process-local) registry that tracks which stream type (snapshot / inference / sensor) is active per device, used to enforce one-stream-slot conflicts (409) and as the fan-out point for live frames. Phase 1 Batch 3 adds StreamType.sensor to it; a Redis-backed version for multi-instance deployments is Phase 11 scope, not this roadmap's.